Guía2. Desarrollo Proyecto APT

Asignatura Capstone

1. Resumen avance Proyecto APT

A continuación, encontrarás distintos campos que deberás completar con la información solicitada.

| Resumen de avance proyecto APT | Project: MORI |
| --- | --- |
| Objetivos | Technical scope: SQL Server was replaced with Supabase (PostgreSQL) to simplify the infrastructure. Removal: The push notifications and local SQLite were removed, as they belong to a native mobile app, not a responsive web app. |
| Metodología | We changed to an overlapping waterfall approach because no significant changes are expected, reducing the overall project time and shortening the global duration. This allows for better resource utilization, as teams can work in parallel across different stages, avoiding idle time. There is an early detection of errors, greater work continuity, and we can avoid waiting between phases, maintaining a more dynamic workflow without losing the structure of the traditional model, while still maintaining project order and control. |
| Evidencias de avance | - Project Charter — 100% - SRS Report (Software Requirements Specification) — 100% - Use Cases (High-Level and Expanded) 100% - DAS Document (Software Architecture) — 100% - Database Model (31 tables) — 100% - UML Diagrams (Use Case, Component, Deployment) 100% - Risk Matrix (52 risks) — 100% - Architectural Patterns Sheet — 100% - Gantt Chart — 100% - Mockups (Figma) — 100% |

| 2. Monitoreo del Plan de Trabajo |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Plan de Trabajo |  |  |  |  |  |  |  |
| Competency Units | Activities | Resources | Duration | Responsible | Observations | Progress Status | Adjustments |
| APT Project | Development of APT project definition | Computer and documents | 11-08-2026 to 17-08-2026 | Dreyco Román | Project was already defined in the final portfolio | Completed | No adjustments |
| Project Management | Project Charter | Computer and documents | 18-08-2026 to 24-08-2026 | Dreyco Román | Example documents were used | Completed | No adjustments |
| Project Management | Requirements Template | Computer and documents | 18-08-2026 to 24-08-2026 | Dreyco Román / Benjamín Concha | Prior requirements definition | Completed | No adjustments |
| Project Management | SRS Report | Computer and documents | 28-08-2026 to 01-09-2026 | Dreyco Román / Benjamín Concha | Templates from previous semesters were used | Completed | No adjustments |
| Prototyping | Mockups | Computer and internet (Figma) | 28-08-2026 to 01-09-2026 | Dreyco Román | Helps determine the final design | Completed | No adjustments |
| Project Management | Gantt Chart | Computer and documents | 25-08-2026 to 01-09-2026 | Dreyco Román | Defines activity dates | Completed | No adjustments |
| Project Management | Expanded Use Cases | Computer and documents | 04-09-2026 to 08-09-2026 | Benjamín Concha / Dreyco Román | Use cases from Architecture were used | Completed | No adjustments |
| Architecture | DAS Document | Computer and documents | 11-09-2026 to 15-09-2026 | Benjamín Concha / Dreyco Román | DAS Architecture document was used | Completed | No adjustments |
| Business | TO-BE Business Process Document | Computer, Bizagi Modeler and documents | 18-09-2026 to 22-09-2026 | Dreyco Román | BPM models were used | Completed | No adjustments |
| Project Management | Data Dictionary | Computer and documents | 25-09-2026 to 29-09-2026 | Rodrigo Riquelme | Facilitates understanding of documents | Completed | No adjustments |
| APT Project | Development of APT project | Computer and documents | 25-09-2026 to 29-09-2026 | Dreyco Román | Adds new development to the proposal | In progress | Technical scope adjusted (Supabase) |
| APT Project | APT Final Report | Computer and documents | 02-10-2026 to 03-10-2026 | Dreyco Román | Explains previous documentation | Completed | No adjustments |
| Databases | Database Model Development | Computer, Supabase, PostgreSQL | 04-10-2026 to 10-10-2026 | Rodrigo Riquelme | Generates the database for the system | Completed | SQL Server replaced with Supabase |
| Programming | 100% System Development | Computer, VS Code, Django, Python, Bootstrap 5, SweetAlert2 | 09-10-2026 to 17-11-2026 | Benjamín Concha / Dreyco Román | Generates 100% of the system | In progress | No adjustments |
| Quality | Test Plan | Computer and documents | 20-11-2026 to 22-11-2026 | Victoria Bahamondes | Tests the quality level of the product | In progress | No adjustments |
| Quality | Change Control Matrix | Computer and documents | 22-11-2026 to 24-11-2026 | Victoria Bahamondes | Facilitates changes during development | In progress | No adjustments |
| Quality | Scope Verification | Computer and documents | 27-11-2026 to 29-11-2026 | Victoria Bahamondes | Checks if the project meets requirements | In progress | No adjustments |
| Project Management | User Manuals | Computer and documents | 28-11-2026 to 07-12-2026 | Dreyco Román / Benjamín Concha | Facilitates system use | In progress | No adjustments |
| Project Management | Project Closure Act | Computer and documents | 29-11-2026 to 08-12-2026 | Dreyco Román | Declares the project as finished | In progress | No adjustments |
| APT Project | APT Presentation Document | Computer and documents | 29-11-2026 to 30-11-2026 | Dreyco Román | Explains the system | In progress | No adjustments |

3. Ajustes a partir del monitoreo

Profundiza en las observaciones de tu plan de trabajo. Analiza las actividades planificadas y señala qué aspectos facilitaron u obstaculizaron la ejecución del plan. Plantea cómo abordaste y/o abordar los obstáculos. Por último, señala los ajustes que realizaste al plan de trabajo a partir de este análisis.

Facilitating Factors: - Prior project definition: The project was already defined from the final portfolio, which saved time during the definition phase and allowed us to start directly with documentation and design. - Use of templates and example documents. - Prior knowledge. - Accessible tools (VS Code / Supabase). - Teamwork: Fluid communication and clear role distribution allowed constant progress without duplicating efforts. - Instructor support: Constant feedback on each deliverable helped correct deviations in time and improve the quality of the deliverables. Challenging Factors: - Limited time availability: Work internships and other courses reduced project time. Action: Managed time with a detailed schedule, prioritized critical tasks, and set fixed weekly work blocks. - Database model complexity: The 31-table design was complex and error-prone. Action: Divided the model into functional modules (Companies, Attendance, Payroll, Documents, Support) for easier understanding and validation.

Adjusted or Removed Activities: Use of FCM for push notifications = Removed Justification: MORI is a responsive web platform, not a native mobile app. FCM push notifications are a technology exclusive to mobile apps. Instead, email notifications (SMTP) and visual alerts within the web panel were implemented using SweetAlert2. Sprint Duration = Adjusted from 3 to 2 weeks Justification: Sprint duration was reduced from 3 to 2 weeks to better fit the academic calendar, allow more iterations, and obtain more frequent feedback from the instructor.

Actividades que no has iniciado o están retrasadas: Test Plan = Not started Reason: It depends on the system being at least 90% developed in order to test all functionalities. Strategy: It will begin in week 13, when system development is complete. A test plan will be prepared including unit, integration, and system tests. Responsible actor: Victoria Bahamondes. Change Control Matrix = Not started Reason: It depends on development progress and on changes arising that need to be documented. Strategy: It will begin in parallel with system development (week 12) and will be updated whenever a significant change is made to the scope or design. Responsible actor: Victoria Bahamondes. Scope Verification = Not started Reason: It depends on the system being complete in order to verify that it meets all the requirements defined in the SRS. Strategy: It will be carried out during the testing phase (week 14), comparing the functional and non-functional requirements with the implemented functionalities. Responsible actor: Victoria Bahamondes. User Manuals = Not started Reason: They depend on the system being stable and having all functionalities implemented. Strategy: They will be prepared during the documentation phase (week 15), including usage guides for each role (administrator, supervisor, employee) and screenshots of the system. Responsible actor: Dreyco Román and Benjamín Concha. Project Closure Act = Not started Reason: It depends on the complete completion of the project. Strategy: It will be prepared in the final week (week 18), once all activities are completed and the system has been delivered. Responsible actor: Dreyco Román. APT Final Presentation = Not started Reason: It depends on the entire project being complete and documented. Strategy: It will be prepared in the final week (week 18), including a functional demonstration of the system and a summary of achievements, challenges, and lessons learned. Responsible actor: The entire team.